## Summary
Tuition Ledger — work estimate
Source of truth: 'Work Breakdown'. Edit Base (hd), Risk, Owner, Status there and capacity/contingency in 'Assumptions'.
Headline
Scope | Base (hd) | Estimate (hd) | Estimate (hours) | Person-days | Done (hd) | % done
MVP | 159 | 193.5 | 774 | 96.75 | 2.2 | 1.137%
Backlog | 96 | 115.2 | 460.8 | 57.6 | 0 | 0%
MVP by role
Role | Base (hd) | Estimate (hd) | Estimate (hours) | Capacity / sprint (hd) | Sprints needed | Weeks needed
BE | 108 | 133.025 | 532.1 | 20 | 6.6513 | 13.3025
FE | 36.5 | 42.5 | 170 | 8 | 5.3125 | 10.625
QA | 7.5 | 8.9 | 35.6 | 2 | 4.45 | 8.9
PM | 7 | 9.075 | 36.3 | 4 | 2.2687 | 4.5375
Critical path (longest role) |  |  |  |  | 6.6513 | 13.3025
MVP load per sprint vs capacity (estimate hd incl. contingency)
Sprint | BE | BE capacity | BE load % | FE | FE capacity | FE load % | QA | PM
S1 | 31.85 | 20 | 159.2% | 10.2 | 8 | 127.5% | 1.1 | 0
S2 | 29.825 | 20 | 149.1% | 12.85 | 8 | 160.6% | 1.2 | 0
S3 | 24.9 | 20 | 124.5% | 4.6 | 8 | 57.5% | 1.8 | 1.35
S4 | 22.3 | 20 | 111.5% | 7.7 | 8 | 96.25% | 2.4 | 3.3
S5 | 24.15 | 20 | 120.8% | 7.15 | 8 | 89.38% | 2.4 | 4.425
Over 100% = that sprint is overloaded; move FE rows to the next sprint or add capacity in Assumptions.
MVP by phase (build order)
Phase | BE (hd) | FE (hd) | QA + PM (hd) | Total estimate (hd) | Hours | Done (hd) | % done
P0 Project setup | 8.2 | 2.75 | 0 | 10.95 | 43.8 | 2.2 | 20.09%
P1 Tenant provisioning | 6.6 | 0 | 0 | 6.6 | 26.4 | 0 | 0%
P2 Authentication & roles | 12.275 | 5.8 | 0 | 18.075 | 72.3 | 0 | 0%
P3 Batches & sessions | 3.6 | 3.3 | 0 | 6.9 | 27.6 | 0 | 0%
P4 Students & enrolments | 2.4 | 2.2 | 0 | 4.6 | 18.4 | 0 | 0%
P5 Attendance | 3.5 | 2.4 | 1.1 | 7 | 28 | 0 | 0%
P6 Fee engine | 11.8 | 1.8 | 0 | 13.6 | 54.4 | 0 | 0%
P7 Ledger & payments | 13.3 | 4.8 | 1.2 | 19.3 | 77.2 | 0 | 0%
P8 WhatsApp messaging | 18.65 | 1.65 | 0.675 | 20.975 | 83.9 | 0 | 0%
P9 Online payments | 6.25 | 2.95 | 2.475 | 11.675 | 46.7 | 0 | 0%
P10 Reminders & digests | 6.4 | 0 | 0 | 6.4 | 25.6 | 0 | 0%
P11 Dashboard, reports & settings | 8.7 | 6.6 | 0 | 15.3 | 61.2 | 0 | 0%
P12 Calendar & rescheduling | 4.2 | 1.1 | 0 | 5.3 | 21.2 | 0 | 0%
P13 Go-live (Gate 2) | 3 | 0 | 5.7 | 8.7 | 34.8 | 0 | 0%
P14 Tests & results | 4.8 | 3 | 0.675 | 8.475 | 33.9 | 0 | 0%
P15 Plans & billing | 8.55 | 3.6 | 0 | 12.15 | 48.6 | 0 | 0%
P16 Hardening & Gate 3 | 10.8 | 0.55 | 6.15 | 17.5 | 70 | 0 | 0%
Total MVP | 133.025 | 42.5 | 17.975 | 193.5 | 774 | 2.2 | 1.137%
Gates
G1 (end S2): September re-entered and the statement balances
G2 (end S4): one live fee cycle, zero duplicate payments
G3 (end S5): first paid invoice

## Assumptions
Estimation assumptions (edit blue cells; everything else recalculates)
Hours per half-day (hd) | 4 | 1 hd = half a working day, as used in docs/09-sprint-plan.md
Working days per sprint | 10 | Two-week sprints (docs/09)
Backend devs | 1 | docs/09 capacity assumption: one backend developer
Frontend devs | 1 | docs/09: one part-time frontend developer
Frontend allocation (fraction of full time) | 40% | Part-time ≈ 8 hd per sprint, matching docs/09 FE totals
QA hd per sprint | 2 | Shared QA (docs/09)
PM hd per sprint | 4 | Shared PM (docs/09)
Contingency by risk
Risk | Contingency % | Meaning
N | 0% | None — reserved capacity or fixed admin task
L | 10% | Low — CRUD / screens with a clear pattern
M | 20% | Medium — some unknowns, moderate integration
H | 35% | High — money correctness, concurrency, external providers, approvals
Capacity per sprint (hd)
BE | 20
FE | 8
QA | 2
PM | 4

## Work Breakdown
Seq | Scope | Phase | Feature | Task ID | Task | Role | Depends on | Sprint | SRS | Design ref | Base (hd) | Risk | Contingency % | Estimate (hd) | Estimate (hours) | Owner | Status | Done when
1 | MVP | P0 Project setup | Monorepo | NEW-01 | Monorepo layout in this repo: /backend, /frontend, /infra; JDK 21 required; root Makefile (up, down, seed, test); .editorconfig; dev-setup section in README | BE | — | S1 | — | 03 §2 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Fresh clone + `make up` works from README steps
2 | MVP | P0 Project setup | Backend skeleton | S1-01 | Backend: Maven (wrapper), Java 21, Spring Boot 4.1, Spring Modulith with 9 modules + shared kernel and ModularityTests | BE | NEW-01 | S1 | — | 04 §0 | 1 | L | 10% | 1.1 | 4.4 |  | Done | `./mvnw test` passes ModularityTests
3 | MVP | P0 Project setup | Frontend skeleton | S1-13a | Frontend: Vite + React 18 + TypeScript strict, ESLint/Prettier, Vitest + Testing Library, React Router, TanStack Query, folder-per-feature (split from S1-13) | FE | NEW-01 | S1 | — | 04 §12, ADR-0014 | 1 | L | 10% | 1.1 | 4.4 |  | Done | `npm run lint`, `test`, `build` all green
4 | MVP | P0 Project setup | Config | NEW-02 | Environment config: Spring profiles dev/test/prod, .env.example, Vite env vars, no secrets in git | BE | S1-01 | S1 | — | 11 | 0.5 | L | 10% | 0.55 | 2.2 |  | In progress | App boots from .env.example values
5 | MVP | P0 Project setup | Local stack | S1-02 | Docker Compose: app, Postgres 16, Redis, Prometheus, Grafana, WhatsApp fake UI; Vite dev proxy to API | BE | S1-01 | S1 | — | 03 §2 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | `make up` brings the stack; /actuator/health green
6 | MVP | P0 Project setup | CI | NEW-03 | GitHub Actions: backend `./mvnw verify` (Testcontainers), frontend lint + test + build, path filters; set both as required checks on protect-main | BE | S1-01, S1-13a | S1 | — | 13 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | PR shows both checks; merge blocked when red
7 | MVP | P0 Project setup | Shared kernel | S1-04 | Shared kernel: Money, ULID Ids, Clock, TenantContext, CentreTime, problem-details handler, ArchUnit no-float rule | BE | S1-01 | S1 | NFR-7 | 04 §1, §11 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Unit tests; ArchUnit rule green
8 | MVP | P0 Project setup | API client | S1-13b | OpenAPI → TypeScript client generation script; CI fails if openapi.yaml changed without regenerating (split from S1-13) | FE | S1-13a, NEW-03 | S1 | — | 06, ADR-0014 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Drift check fails CI on purpose-made mismatch
9 | MVP | P0 Project setup | Design system | S1-13c | Design tokens + base components: button, input, form field with server errors, list/table, money formatter with tabular numerals (split from S1-13) | FE | S1-13a | S1 | NFR-6 | 04 §12 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | Components render at 360 px
10 | MVP | P0 Project setup | Ops baseline | S1-16 | Nightly pg_dump to object storage, restore script, Uptime Kuma, Grafana v0, alert to phone on health down | BE | S1-02 | S1 | NFR-4 | 12 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Restore into a fresh container demonstrated and logged
11 | MVP | P1 Tenant provisioning | Schema | S1-03 | Flyway baseline tenant tables (centres, users, settings, audit_log, batches, sessions, students, enrolments, attendance, holidays) with RLS policies and tl_app grants | BE | S1-01 | S1 | — | 05 | 2 | H | 35% | 2.7 | 10.8 |  | Not started | Migrations idempotent; UPDATE on audit_log fails in a test
12 | MVP | P1 Tenant provisioning | Centre creation | NEW-04 | Centre provisioning: platform-admin endpoint + CLI command creating centre, owner user and default settings; validates CEN-1 fields (timezone, due day, quiet hours, receipt prefix) | BE | S1-03, S1-04 | S1 | CEN-1, PLT-1 | 04 §2, 07 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | New centre + owner created in one call; invalid prefix rejected
13 | MVP | P1 Tenant provisioning | Isolation | S1-07 | Tenant isolation: Hibernate filter, @TenantScoped, SET LOCAL app.centre_id, entity-scan test, native-query allow-list | BE | S1-03, NEW-04 | S1 | NFR-8 | 03 §4 | 2 | H | 35% | 2.7 | 10.8 |  | Not started | Two centres: every repository returns own rows only; RLS blocks raw query
14 | MVP | P2 Authentication & roles | Auth API | S1-05 | OTP via WhatsApp (Redis), JWT + refresh rotation with reuse detection, /auth/*, /me, invite / change role / deactivate users | BE | S1-07 | S1 | CEN-2, CEN-4 | 04 §2 | 3 | H | 35% | 4.05 | 16.2 |  | Not started | OTP expiry, 3-attempt lock, rotation tests; deactivated user → 401 within 60 s
15 | MVP | P2 Authentication & roles | Permissions | S1-06 | Permission enum, role matrix from 07, @PreAuthorize wiring, teacher batch scoping, matrix-equality test | BE | S1-05 | S1 | CEN-3 | 04 §2, 07 §1 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Every (role, permission) matches 07; teacher on other batch → 403
16 | MVP | P2 Authentication & roles | Audit | S1-11 | Audit aspect and /audit endpoint | BE | S1-05 | S1 | NFR-5 | 04 §2 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | Settings change writes before/after audit row
17 | MVP | P2 Authentication & roles | Login UI | S1-13d | FE login: phone, OTP, resend timer, error states, token storage and silent refresh (split from S1-13) | FE | S1-05, S1-13b, S1-13c | S1 | CEN-2 | 06 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Login on 360 px; refresh invisible to the user
18 | MVP | P2 Authentication & roles | App shell | S1-13e | FE app shell: role-based navigation, route guards, 401/403 pages (split from S1-13) | FE | S1-13d, S1-06 | S1 | CEN-3 | 04 §12 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Teacher sees only teacher menu
19 | MVP | P2 Authentication & roles | Staff UI | NEW-05 | FE staff management: list, invite, change role, deactivate | FE | S1-13e | S2 | CEN-4 | 07 §1 | 1.5 | L | 10% | 1.65 | 6.6 |  | Not started | Invite → staff can log in; deactivate → logged out
20 | MVP | P2 Authentication & roles | Self-serve signup | NEW-10 | Registration API: POST /signup/otp + /signup (centre name, owner, email, WhatsApp number, password), OTP before any row, unique phone/email, 3 per phone/email/IP per day, 30-day trial; reuses NEW-04 provisioning | BE | NEW-04, S1-05 | S2 | CEN-6 | ADR-0018, 06 | 1.5 | H | 35% | 2.025 | 8.1 |  | Not started | No centre row before OTP; duplicate phone/email refused; 4th signup per IP → 429
21 | MVP | P2 Authentication & roles | Email + password | NEW-11 | Email + password sign-in: POST /auth/login, Argon2id, common-password list, 5-failure lock + WhatsApp notice, email verification, forgot/reset (email link or WhatsApp code), PATCH /me/credentials; transactional email provider | BE | S1-05 | S2 | CEN-2, CEN-8 | ADR-0019, 11 | 2 | H | 35% | 2.7 | 10.8 |  | Not started | Lock after 5 failures; used reset link refused; sessions revoked on reset
22 | MVP | P2 Authentication & roles | Signup + login UI | NEW-12 | FE registration + OTP step, sign-in by WhatsApp code or email + password, forgot/reset screens, My account sign-in methods | FE | NEW-10, NEW-11, S1-13d | S2 | CEN-2, CEN-6, CEN-8 | design/prototype.html | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Both sign-in methods land on the same role; screens match the prototype
23 | MVP | P3 Batches & sessions | Batches API | S1-08 | Batches CRUD, schedule value object, session generation job with holidays, extra/cancel session | BE | S1-06 | S1 | BAT-1..3 | 04 §3 | 3 | M | 20% | 3.6 | 14.4 |  | Not started | Re-running generation creates no duplicates
24 | MVP | P3 Batches & sessions | Batches UI | S1-14a | FE batches: list, create/edit with schedule, teacher and fee plan (split from S1-14) | FE | S1-08, S1-13e | S1 | BAT-1 | 06 | 1.5 | L | 10% | 1.65 | 6.6 |  | Not started | Server field errors shown inline
25 | MVP | P3 Batches & sessions | Sessions UI | NEW-06 | FE sessions and holidays: week view, add extra / cancel session, holiday list | FE | S1-08, S1-13e | S2 | BAT-2, BAT-3 | 06 | 1.5 | L | 10% | 1.65 | 6.6 |  | Not started | Cancelled session disappears from attendance list
26 | MVP | P4 Students & enrolments | Students API | S1-09 | Students CRUD, E.164 validation, enrolments with exclusion constraint, status change events | BE | S1-07 | S1 | STU-1, ENR-1, ENR-2 | 04 §4 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Overlapping enrolment rejected; capacity override audited
27 | MVP | P4 Students & enrolments | Students UI | S1-14b | FE students: list, search, create/edit with E.164, enrol in batch (split from S1-14) | FE | S1-09, S1-13e | S1 | STU-1 | 06 | 1.5 | L | 10% | 1.65 | 6.6 |  | Not started | Forms validate E.164
28 | MVP | P4 Students & enrolments | Status UI | NEW-07 | FE student status changes (pause, leave, resume) and enrolment history | FE | S1-14b | S2 | STU-2, ENR-2 | 06 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Status change visible in history
29 | MVP | P5 Attendance | Attendance API | S1-10 | Mark with supersede, 7-day window, month view query | BE | S1-08, S1-09 | S1 | ATT-1, ATT-2 | 04 §3 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Second save keeps history; day-8 edit → 409
30 | MVP | P5 Attendance | Attendance UI | S1-15 | FE attendance marking, phone-first (default present, tap to toggle, save, offline warning) | FE | S1-10, S1-13e | S1 | ATT-1 | 06 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | 40 students marked in under 60 s
31 | MVP | P5 Attendance | Seed data | S1-12 | Seed script: Bright Minds, 3 teachers, 7 batches, 118 students, 2 months of attendance | BE | S1-10 | S1 | — | 03 §10 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | `make seed` under 30 s
32 | MVP | P5 Attendance | QA | S1-17 | QA: sprint 1 test matrix; exploratory session on attendance | QA | S1-15 | S1 | — | 10 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | Findings filed as issues
33 | MVP | P6 Fee engine | Schema | S2-01 | Migrations: charges, fee_runs, receipt_counters, payments, allocations, ledger_lines, mv_student_balances, grants | BE | S1-03 | S2 | — | 05 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Applied; grants tested
34 | MVP | P6 Fee engine | Calculator | S2-02 | FeeCalculator: pro-ration, discount, single rounding, computation JSON; jqwik properties | BE | S1-04 | S2 | FEE-2, FEE-5 | 04 §5 | 2 | H | 35% | 2.7 | 10.8 |  | Not started | SRS examples pass; split-month property holds
35 | MVP | P6 Fee engine | Fee run | S2-03 | Fee run job per centre: ShedLock, paging, per-student transactions, progress, manual run/resume endpoint | BE | S2-02 | S2 | FEE-1, FEE-3 | 04 §5, 03 §7 | 3 | H | 35% | 4.05 | 16.2 |  | Not started | Run twice → same count; kill at 60/118 and resume → 118
36 | MVP | P6 Fee engine | Fee run preview | NEW-13 | GET /fee-runs/{period}/preview: dry run with computation, writes nothing | BE | S2-03 | S2 | FEE-1 | 06 | 0.5 | M | 20% | 0.6 | 2.4 |  | Not started | Preview equals the charges the run then creates
37 | MVP | P6 Fee engine | Adjustments | S2-04 | Adjustments from StatusChanged / EnrolmentChanged (pause, leave, mid-month join, plan change) | BE | S2-03 | S2 | STU-2, FEE-6 | 04 §5 | 2 | H | 35% | 2.7 | 10.8 |  | Not started | Pause on 16th of 30-day month → −15/30
38 | MVP | P6 Fee engine | One-off charges | S2-05 | One-off charges endpoint | BE | S2-01 | S2 | FEE-4 | 06 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Appears in ledger with description
39 | MVP | P6 Fee engine | Fee run UI | S2-13 | FE fee run page (preview, progress, resume) and one-off charge form | FE | S2-03 | S2 | FEE-1 | 06 | 1.5 | M | 20% | 1.8 | 7.2 |  | Not started | Progress 60/118 visible during run
40 | MVP | P7 Ledger & payments | Ledger | S2-06 | LedgerLine append, balance query, materialised view refresh with debounce | BE | S2-01 | S2 | LED-1 | 04 §6 | 2 | H | 35% | 2.7 | 10.8 |  | Not started | View equals sum after refresh
41 | MVP | P7 Ledger & payments | Payments | S2-07 | PaymentService.record: idempotency key, near-duplicate check, receipt counter lock, oldest-first allocation, credit | BE | S2-06 | S2 | PAY-1, PAY-3, PAY-4, LED-2 | 04 §6, ADR-0006/7 | 3 | H | 35% | 4.05 | 16.2 |  | Not started | Replay → same receipt; 50-thread test → 1..50
42 | MVP | P7 Ledger & payments | Refunds | S2-08 | Refund and reallocation endpoints with reasons | BE | S2-07 | S2 | PAY-5 | 04 §6 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Originals unchanged; refund line referenced
43 | MVP | P7 Ledger & payments | Adjustments API | NEW-14 | POST /adjustments: signed discount/credit/correction with required reason | BE | S2-06 | S2 | PAY-5 | 06 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Adds a ledger line; nothing edited
44 | MVP | P7 Ledger & payments | Statement | S2-09 | Monthly statement and nightly reconciliation job (tl_reconciliation_diff_paise) | BE | S2-07 | S2 | LED-3 | 04 §9 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Equation holds on seed data
45 | MVP | P7 Ledger & payments | Events | S2-10 | Modulith event publication registry (JDBC), replay incomplete on startup | BE | S2-07 | S2 | — | ADR-0011 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Kill between commit and listener → runs on restart
46 | MVP | P7 Ledger & payments | Ledger UI | S2-11 | FE student ledger with running balance; charge explanation popover | FE | S2-07 | S2 | LED-1, FEE-5 | 06 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Matches API totals
47 | MVP | P7 Ledger & payments | Payment UI | S2-12 | FE record payment (cash, UTR) with client UUID, near-duplicate dialog, receipt view | FE | S2-07 | S2 | PAY-1, PAY-3 | 06 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Double-tap creates one payment
48 | MVP | P7 Ledger & payments | QA | NEW-08 | QA: money matrix (pro-ration cases, duplicates, refunds, statement equation) | QA | S2-12 | S2 | — | 10 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Executed; defects filed
49 | MVP | P7 Ledger & payments | Gate 1 | S2-14 | Gate 1: re-enter September from the register with the accountant; log discrepancies | BE | S2-12 | S2 | — | 01 §10 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Statement balances
50 | MVP | P8 WhatsApp messaging | Schema | S3-01 | Migrations: message_templates, outbox_messages, inbound_messages, webhook_events, consents, opt_outs, payment_links | BE | S2-01 | S3 | — | 05 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Applied
51 | MVP | P8 WhatsApp messaging | Templates | S3-02 | Template table + renderer with snapshot tests; English templates | BE | S3-01 | S3 | MSG-2, STU-3 | 04 §7, 01 §5 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Snapshots match 01 §5
52 | MVP | P8 WhatsApp messaging | Template approval | S3-13 | Submit templates to Meta for approval (3–5 business days lead time) | PM | S3-02 | S3 | MSG-2 | ADR-0010 | 0.5 | H | 35% | 0.675 | 2.7 |  | Not started | Approval IDs recorded
53 | MVP | P8 WhatsApp messaging | Outbox | S3-03 | Outbox enqueue with dedupe key + not_before; relay with SKIP LOCKED, backoff; PreSendChecks | BE | S3-02 | S3 | MSG-4, MSG-5, MSG-7 | 04 §7 | 3 | H | 35% | 4.05 | 16.2 |  | Not started | Kill relay mid-batch → each row sent once
54 | MVP | P8 WhatsApp messaging | WhatsApp adapter | S3-04 | Meta Cloud client with Resilience4j, fake client, status + inbound webhooks with signature check | BE | S3-03 | S3 | MSG-4, MSG-6 | 04 §8 | 3 | H | 35% | 4.05 | 16.2 |  | Not started | Bad signature → 401; status updates delivery
55 | MVP | P8 WhatsApp messaging | Consent | S3-05 | Opt-in on StudentAdded, YES → consent, STOP → opt-out + owner notified | BE | S3-04 | S3 | STU-3, MSG-7 | 04 §4 | 1.5 | M | 20% | 1.8 | 7.2 |  | Not started | No reminder possible before consent
56 | MVP | P8 WhatsApp messaging | Keywords | S3-06 | Inbound router: DUES, ATTENDANCE, RECEIPT, HELP, unknown → owner; Bengali synonyms | BE | S3-04 | S3 | MSG-6, ATT-3 | 04 §7 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Reply content test per keyword
57 | MVP | P8 WhatsApp messaging | Receipts | S3-07 | Receipt message on PaymentRecorded; 60-second SLA metric | BE | S3-03 | S3 | MSG-2 | 04 §7 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | Receipt row enqueued in listener
58 | MVP | P8 WhatsApp messaging | Message log | S3-10 | Message log per student; owner inbox for forwarded replies | BE | S3-06 | S3 | MSG-6 | 06 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | Log shows template, variables, status
59 | MVP | P8 WhatsApp messaging | Sender status | NEW-15 | Centre WhatsApp sender status (not_connected/pending/connected), embedded signup start, outbox `held` released on approval | BE | S3-03, S3-04 | S3 | CEN-7 | ADR-0018 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Receipt recorded before approval is held, then sent on approval
60 | MVP | P8 WhatsApp messaging | Consent UI | S3-11 | FE consent status on students, resend opt-in, verbal consent with timestamp | FE | S3-05 | S3 | STU-3 | 06 | 1.5 | L | 10% | 1.65 | 6.6 |  | Not started | States visible and actionable
61 | MVP | P9 Online payments | KYC | S3-14 | Start Razorpay KYC for pilot centre (≈1 week lead time — start in sprint 1) | PM | — | S3 | PAY-2 | 08 | 0.5 | H | 35% | 0.675 | 2.7 |  | Not started | Live keys by sprint 4
62 | MVP | P9 Online payments | Razorpay adapter | S3-08 | Payment link create; payment_link.paid webhook with signature; event store; PaymentService call | BE | S2-07 | S3 | PAY-2 | 04 §8, ADR-0006 | 3 | H | 35% | 4.05 | 16.2 |  | Not started | Replayed webhook → one payment
63 | MVP | P9 Online payments | Links API | S3-09 | Payment links endpoint with plan gate stub; short URL in reminders | BE | S3-08 | S3 | PAY-2 | 06 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | Link created in sandbox
64 | MVP | P9 Online payments | Links + inbox UI | S3-12 | FE payment link from student page / outstanding list; message log tab; owner inbox | FE | S3-09, S3-10 | S3 | PAY-2, MSG-6 | 06 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Link copied/shared; inbox reply box
65 | MVP | P9 Online payments | Announcements API | S3-16 | Batch announcements: endpoint, template, per-parent fan-out via outbox; auto-announce on cancel | BE | S3-03 | S3 | ANN-1, ANN-2 | 04 §7 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | Opt-out skipped
66 | MVP | P9 Online payments | Announcements UI | S3-17 | FE announcement composer with recipient count and preview | FE | S3-16 | S3 | ANN-1 | 06 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Count matches API
67 | MVP | P9 Online payments | QA | S3-15 | QA: webhook replay, outbox crash, quiet hours, keyword matrix | QA | S3-08 | S3 | — | 10 | 1.5 | M | 20% | 1.8 | 7.2 |  | Not started | Executed; defects filed
68 | MVP | P10 Reminders & digests | Reminders | S4-01 | Reminder scheduler: slots, per-charge dedupe, live-balance check at enqueue and send, sibling combination | BE | S3-03 | S4 | MSG-1, MSG-8 | 04 §7, ADR-0008 | 3 | H | 35% | 4.05 | 16.2 |  | Not started | Pay at 07:58 → skipped; two children → one message
69 | MVP | P10 Reminders & digests | Digest | S4-02 | Weekly digest job with disable setting; sibling combination | BE | S4-01 | S4 | MSG-3 | 04 §7 | 1.5 | M | 20% | 1.8 | 7.2 |  | Not started | No digest when disabled
70 | MVP | P10 Reminders & digests | Send now | S4-03 | 'Send reminder now' with 24-hour per-parent limit | BE | S4-01 | S4 | RPT-2 | 06 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Second call → 429
71 | MVP | P11 Dashboard, reports & settings | Dashboard API | S4-04 | Dashboard queries on mv + indexes; < 100 ms on seed | BE | S2-06 | S4 | RPT-1 | 04 §9 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Every figure matches SQL in test
72 | MVP | P11 Dashboard, reports & settings | Reports API | S4-05 | Outstanding list with days overdue; streaming CSV exports | BE | S4-04 | S4 | RPT-2, RPT-3 | 06 | 1.5 | M | 20% | 1.8 | 7.2 |  | Not started | 10k rows stream without OOM
73 | MVP | P11 Dashboard, reports & settings | List summaries | NEW-16 | Students list filters hasBalance/consent + batchIds/attendanceRate30d; batch list summary fields | BE | S1-09, S1-08 | S4 | STU-1, BAT-1 | 06 | 1 | L | 10% | 1.1 | 4.4 |  | Not started | One request per list screen; no N+1
74 | MVP | P11 Dashboard, reports & settings | Low attendance | S4-06 | Low-attendance flag job | BE | S1-10 | S4 | ATT-4 | 04 §3 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Flag appears next morning
75 | MVP | P11 Dashboard, reports & settings | Settings API | S4-07 | Centre settings endpoints + audit for all of 07 §2 | BE | S1-11 | S4 | CEN-1 | 07 | 1.5 | L | 10% | 1.65 | 6.6 |  | Not started | Each change audited and effective
76 | MVP | P11 Dashboard, reports & settings | Receipt PDF | S4-18 | Receipt PDF: HTML template, renderer, signed 90-day link, object storage | BE | S3-07 | S4 | RCP-1 | 04 §9 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | PDF totals equal ledger
77 | MVP | P11 Dashboard, reports & settings | Dashboard UI | S4-09 | FE dashboard, outstanding list with send-now, reports with statement and exports | FE | S4-04 | S4 | RPT-1..3 | 06 | 3 | M | 20% | 3.6 | 14.4 |  | Not started | Figures match API; phone layout
78 | MVP | P11 Dashboard, reports & settings | Settings UI | S4-10 | FE settings (07 §2), audit log viewer, onboarding checklist | FE | S4-07 | S4 | CEN-1 | 07 | 2.5 | M | 20% | 3 | 12 |  | Not started | Checklist completes on seed centre
79 | MVP | P12 Calendar & rescheduling | iCal feeds | S4-14 | iCal feed per user, signed token, revoke/rotate, deep link | BE | S1-08 | S4 | CAL-1, CAL-2 | ADR-0015 | 1.5 | M | 20% | 1.8 | 7.2 |  | Not started | Subscribes in Google Calendar; revoked → 404
80 | MVP | P12 Calendar & rescheduling | Nudges | S4-15 | Teacher pre-session WhatsApp nudge via outbox, cancelled on cancel / already marked | BE | S3-03 | S4 | CAL-3 | 04 §7 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Timing and cancellation tests
81 | MVP | P12 Calendar & rescheduling | Reschedule API | S4-17 | Session reschedule with history; nudges, feeds, announcement follow | BE | S4-14 | S4 | SCH-1, ANN-2 | 04 §3 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Feed and nudge at new time
82 | MVP | P12 Calendar & rescheduling | Calendar UI | S4-16 | FE 'Add to my calendar' page and nudge settings | FE | S4-14 | S4 | CAL-4 | 07 §2 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Works on phone
83 | MVP | P12 Calendar & rescheduling | Reschedule UI | S4-19 | FE reschedule dialog; all-batches announcement with preview | FE | S4-17 | S4 | SCH-1, ANN-3 | 06 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | —
84 | MVP | P13 Go-live (Gate 2) | Observability | S4-08 | Metrics + alerts (outbox age, skipped reminders, fee run, webhook failures); Grafana v1 | BE | S3-03 | S4 | NFR | 03 §9, 12 | 1.5 | M | 20% | 1.8 | 7.2 |  | Not started | Alerts fire in a drill
85 | MVP | P13 Go-live (Gate 2) | Production deploy | NEW-09 | Production VPS: reverse proxy + TLS, frontend static build served, deploy job on merge to main | BE | NEW-03 | S4 | NFR-3 | 03 §2, 12 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | https URL serves SPA + API; deploy from main only
86 | MVP | P13 Go-live (Gate 2) | QA | S4-13 | QA: reminder matrix, dashboard figures, settings effects | QA | S4-09 | S4 | — | 10 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Executed; defects filed
87 | MVP | P13 Go-live (Gate 2) | Go-live | S4-11 | Go-live runbook for Bright Minds: live WhatsApp sender, Razorpay live keys, backups, staff onboarded, opt-ins | PM | S4-01, NEW-09 | S4 | — | 12 | 2 | H | 35% | 2.7 | 10.8 |  | Not started | Checklist signed
88 | MVP | P13 Go-live (Gate 2) | Live fee run | S4-12 | Fee run on the 1st with owner present; register as control | PM | S4-11 | S4 | — | 01 §10 | 0.5 | M | 20% | 0.6 | 2.4 |  | Not started | Run complete; discrepancies logged
89 | MVP | P14 Tests & results | Marks API | S5-15 | Tests and marks: append-only with supersede, 14-day window, teacher scoping | BE | S1-10 | S5 | ASM-1, ASM-2 | 04 §3 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Marks history test; above-max rejected
90 | MVP | P14 Tests & results | Send results | S5-16 | Per-child result messages, consent checks, batch average setting, once-per-test guard, correction | BE | S3-03 | S5 | ASM-3, ASM-4 | 04 §7 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Resend → 409; correction → one parent
91 | MVP | P14 Tests & results | Marks UI | S5-17 | FE tests list, marks entry on phone, send-results confirmation | FE | S5-15 | S5 | ASM-1..3 | 06 | 2.5 | M | 20% | 3 | 12 |  | Not started | 40 students under 90 s
92 | MVP | P14 Tests & results | Template approval | S5-18 | Result templates submitted to Meta | PM | S3-13 | S5 | ASM-3 | ADR-0016 | 0.5 | H | 35% | 0.675 | 2.7 |  | Not started | Approved before S5-16 ships
93 | MVP | P15 Plans & billing | PlanGuard | S5-02 | Platform module: plans, subscriptions, PlanGuard with Redis snapshot, limits in services and relay | BE | S1-05 | S5 | PLT-1, MSG-9 | 04 §10, ADR-0012 | 2.5 | H | 35% | 3.375 | 13.5 |  | Not started | 402s per 08 §2
94 | MVP | P15 Plans & billing | Metering | S5-03 | Metering job, platform invoices, Razorpay subscription/link, grace → read-only → suspended | BE | S5-02 | S5 | PLT-2, PLT-3 | 08 §3 | 2.5 | H | 35% | 3.375 | 13.5 |  | Not started | Bright Minds invoice = ₹235 + GST
95 | MVP | P15 Plans & billing | Console API | S5-04 | Platform console API (counts only) and audited 30-min support session | BE | S5-02 | S5 | PLT-1 | 07 §5 | 1.5 | M | 20% | 1.8 | 7.2 |  | Not started | No student names in any response
96 | MVP | P15 Plans & billing | Plans + console UI | S5-10 | FE plan & usage page, upgrade/downgrade, read-only banner, platform console screens incl. create centre | FE | S5-02, NEW-04 | S5 | PLT-1..4 | 06, 07 §5 | 3 | M | 20% | 3.6 | 14.4 |  | Not started | Upgrade flow in sandbox
97 | MVP | P16 Hardening & Gate 3 | Data deletion | S5-06 | Personal-data deletion endpoint and retention job | BE | S2-07 | S5 | STU-6 | 11 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Placeholders; ledger intact
98 | MVP | P16 Hardening & Gate 3 | Deletion UI | S5-11a | FE data deletion confirmation (CSV import wizard moved to backlog with S5-05) | FE | S5-06 | S5 | STU-6 | 06 | 0.5 | L | 10% | 0.55 | 2.2 |  | Not started | Confirmation names the student
99 | MVP | P16 Hardening & Gate 3 | Load test | S5-08 | k6 load test 300 centres × 150 students; fix hot spots | BE | S4-04 | S5 | NFR-1, NFR-2 | 03 §8 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Report in docs/perf
100 | MVP | P16 Hardening & Gate 3 | Security | S5-09 | Restore drill and security pass (dependency, headers, rate limits, secrets scan) | BE | — | S5 | NFR-4 | 11, 12 | 1 | M | 20% | 1.2 | 4.8 |  | Not started | Drill logged; scan clean
101 | MVP | P16 Hardening & Gate 3 | Pilot fixes | S5-01 | Pilot fixes — reserved capacity (already a buffer, so no contingency added) | BE | S4-12 | S5 | — | — | 6 | N | 0% | 6 | 24 |  | Not started | Each fix has a regression test
102 | MVP | P16 Hardening & Gate 3 | Google verification | S5-14 | Start Google OAuth app verification for sprint-6 sync | PM | — | S5 | CAL-5 | ADR-0015 | 1 | H | 35% | 1.35 | 5.4 |  | Not started | Submitted
103 | MVP | P16 Hardening & Gate 3 | QA | S5-13 | QA: full regression, plan-limit matrix, console privacy check | QA | S5-10 | S5 | — | 10 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Executed; release notes
104 | MVP | P16 Hardening & Gate 3 | Gate 3 | S5-12 | Onboard two more centres; collect first invoice; write case study | PM | S5-03 | S5 | — | 01 §10 | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Invoice paid
105 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-01 | Monthly assessment with teacher comment | BE/FE | MVP | Phase 2 | ASM-5..8 | 15-roadmap | 6 | M | 20% | 7.2 | 28.8 |  | Not started | Not committed — size from 15-roadmap.md
106 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-02 | Admissions pipeline | BE/FE | MVP | Phase 2 | ADM-1..4 | 15-roadmap | 6 | M | 20% | 7.2 | 28.8 |  | Not started | Not committed — size from 15-roadmap.md
107 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-03 | Homework and study material | BE/FE | MVP | Phase 2 | HWK-1..2 | 15-roadmap | 4 | M | 20% | 4.8 | 19.2 |  | Not started | Not committed — size from 15-roadmap.md
108 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-04 | Parent leave requests (LEAVE keyword) | BE/FE | MVP | Phase 2 | LVE-1..2 | 15-roadmap | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Not committed — size from 15-roadmap.md
109 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-05 | Expenses and profit view | BE/FE | MVP | Phase 2 | EXP-1..3 | 15-roadmap | 5 | M | 20% | 6 | 24 |  | Not started | Not committed — size from 15-roadmap.md
110 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-06 | Accountant exports (Tally, Zoho, GST) | BE/FE | MVP | Phase 2 | ACC-1..2 | 15-roadmap | 3 | M | 20% | 3.6 | 14.4 |  | Not started | Not committed — size from 15-roadmap.md
111 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-07 | Google Calendar sync and conflict checks | BE/FE | MVP | Phase 2 | CAL-5 | 15-roadmap | 6.5 | M | 20% | 7.8 | 31.2 |  | Not started | Not committed — size from 15-roadmap.md
112 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-08 | CSV student import (S5-05 + wizard), Bengali templates | BE/FE | MVP | Phase 2 | STU-5, MSG-2 | 15-roadmap | 2.5 | M | 20% | 3 | 12 |  | Not started | Not committed — size from 15-roadmap.md
113 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-09 | Bank statement import and matching | BE/FE | MVP | Phase 2 | BNK-1 | 15-roadmap | 3 | M | 20% | 3.6 | 14.4 |  | Not started | Not committed — size from 15-roadmap.md
114 | Backlog | Phase 2 · post-pilot | Roadmap item | BL-10 | Teacher payroll share | BE/FE | MVP | Phase 2 | PAYR-1 | 15-roadmap | 2 | M | 20% | 2.4 | 9.6 |  | Not started | Not committed — size from 15-roadmap.md
115 | Backlog | Phase 3 · growth | Roadmap item | BL-11 | QR self check-in | BE/FE | MVP | Phase 3 | QR-1..2 | 15-roadmap | 5 | M | 20% | 6 | 24 |  | Not started | Not committed — size from 15-roadmap.md
116 | Backlog | Phase 3 · growth | Roadmap item | BL-12 | Parent–teacher meeting slots | BE/FE | MVP | Phase 3 | PTM-1..2 | 15-roadmap | 4 | M | 20% | 4.8 | 19.2 |  | Not started | Not committed — size from 15-roadmap.md
117 | Backlog | Phase 3 · growth | Roadmap item | BL-13 | Multi-branch centres | BE/FE | MVP | Phase 3 | MB-1..3 | 15-roadmap | 10 | M | 20% | 12 | 48 |  | Not started | Not committed — size from 15-roadmap.md
118 | Backlog | Phase 3 · growth | Roadmap item | BL-14 | Referral programme | BE/FE | MVP | Phase 3 | REF-1 | 15-roadmap | 3 | M | 20% | 3.6 | 14.4 |  | Not started | Not committed — size from 15-roadmap.md
119 | Backlog | Phase 3 · growth | Roadmap item | BL-15 | Vernacular staff UI (Bengali, Hindi) | BE/FE | MVP | Phase 3 | I18N-1 | 15-roadmap | 6 | M | 20% | 7.2 | 28.8 |  | Not started | Not committed — size from 15-roadmap.md
120 | Backlog | Phase 4 · add-ons | Roadmap item | BL-16 | Recorded class library + student portal | BE/FE | MVP | Phase 4 | VID-1..7 | 15-roadmap | 20 | M | 20% | 24 | 96 |  | Not started | Not committed — size from 15-roadmap.md
121 | Backlog | Phase 4 · add-ons | Roadmap item | BL-17 | Multilingual everything | BE/FE | MVP | Phase 4 | I18N-2..3 | 15-roadmap | 8 | M | 20% | 9.6 | 38.4 |  | Not started | Not committed — size from 15-roadmap.md
Note on L1: Base size from docs/09-sprint-plan.md (hd = half-day). NEW-xx and split rows are estimates added in this sheet.

## How to use
How to use this workbook
1. 'Work Breakdown' lists every task in build order (Seq). Tenant provisioning comes before auth; each backend API comes before the screen that uses it.
2. Yellow cells are yours to edit: Base (hd), Risk (N/L/M/H), Owner, Status. Blue text = input values.
3. Estimate (hd) = Base × (1 + contingency for the risk level). Hours = Estimate × hours per hd (Assumptions).
4. 'Summary' recalculates totals, sprints needed per role, per-sprint load vs capacity, and % done from Status.
5. Task IDs: S#-## = ticket from docs/09-sprint-plan.md; S1-13a..e / S1-14a,b / S5-11a = tickets split for clarity; NEW-## = work missing from the sprint plan; BL-## = roadmap backlog (not committed).
6. Example row: Seq 14 · S1-05 · BE · Base 3 hd · Risk H → 3 × 1.35 = 4.05 hd ≈ 16 h.
Repo layout assumed (monorepo, this repo): /backend (Spring Boot, Gradle), /frontend (React + Vite), /infra (Docker Compose, deploy), /docs.
Branching: every task = one branch + one PR into main (main is protected).